## Sprint 1
SPRINT 1 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
13 | Set up Java environment for software development | 13.1 | Have Eclipse IDE installed on all developer's computer | Team |  |  | ü
14 | Update JDK to latest version | 14.1 | Update IDE Java environment to latest version | Team |  |  | ü
15 | Set up Git repository for version control | 15.1 | Set up private git repository | Wee Jueh |  |  | ü
|  | 15.2 | Invite all developers to collaborate in git project | Wee Jueh |  |  | ü
|  | 15.3 | Create skeleton structure of program with reference to class diagram | Wee Jueh |  |  | ü
16 | Design UML diagram | 16.1 | Create sequence diagram for enrol sequence | So Yeun |  |  | ü
|  | 16.2 | Create sequence diagram for withdraw sequence | So Yeun |  |  | ü
|  | 16.3 | Create sequence diagram for course list view sequence | So Yeun |  |  | ü
|  | 16.4 | Create sequence diagram for course figure view sequence | So Yeun |  |  | ü
17 | Design class diagram | 17.1 | Propose classes needed | Wee Jueh |  |  | ü
|  | 17.2 | Propose data structures needed | Wee Jueh |  |  | ü
18 | Develop console menu for the program | 18.1 | Develop main driver class | Alex |  |  | ü
|  | 18.2 | Develop main menu print function | Alex |  |  | ü
19 | Develop method to navigate program | 19.1 | Develop function to receive user input | Alex |  |  | ü
21 | Implement error handling functions for handling invalid inputs | 21.1 | Develop function to check for erroneous input from user | Alex |  |  | ü
23 | Implement course attributes | 23.1 | Create interface and abstract class for course | So Yeun |  |  | ü
|  | 23.2 | Implement course class attribute | So Yeun |  |  | ü
33 | Implement financial details for each course | 33.1 | Develop profit and income calculation function | So Yeun |  |  | ü
5 | As a course manager, I want to be able to display a list of existing courses so that I can review the course details | 5.1 | Develop function to calculate financial figures of courses | So Yeun |  |  | ü
|  | 5.2 | Develop function to display list of course to console | So Yeun |  |  | ü
10 | As a course manager, I want to be able to see the overall profit a course is making | 10.1 | Develop function to calculate course figures | So Yeun |  |  | ü

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #NAME? | #NAME?
| Previous Year | #NAME? | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!