## Sprint 2
SPRINT 2 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
20 | Develop function to enrol student to a course | 20.1 | Develop function to take student details input from course manager | Alex |  |  | ü | Implemented with PBI 1 and 2
|  | 20.2 | Develop function to check for enrolment in current course | Alex |  |  | ü
24 | Implement error handling when trying to enrol in a course | 24.1 | Develop function to check for erroneous inputs | Alex |  |  | ü
25 | Implement database for storing student enrolment records | 25.1 | Implement serialization for course object | Wee Jueh |  |  | ü
|  | 25.2 | Implement saving of data from serialised file | Wee Jueh |  |  | ü
|  | 25.3 | Implement reading of data from serialised file | Wee Jueh |  |  | ü
22 | Implement specific limits for courses | 22.1 | Create courses with default limit values | So Yeun |  |  | ü | Implemented with PBI 8
4 | As a course manager, I want to be able to display list of students in a course so that I can view students currently enrolled in a course | 4.1 | Develop function to received course id input from course manager | So Yeun |  |  | ü
|  |  | Develop function to check input against existing course id | So Yeun |  |  | ü
|  |  | Develop function to print all student details to screen | So Yeun |  |  | ü
26 | Develop function to link new student enrolment to previous details | 26.1 | Develop function to keep record of past students | So Yeun |  |  | ü
27 | Develop function to look for past enrolments of eligibility of discount | 27.1 | Develop function to set past enrolment | So Yeun |  |  | ü | Implemented with PBI 7
|  |  | Develop function to apply discount | So Yeun |  |  | ü

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #NAME? | #NAME?
| Previous Year | #NAME? | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!