## Sprint 3
SPRINT 3 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
3 | As a course manager, I want to be able to withdraw students from courses so that I can maintain correct enrolment details | 3.1 | Develop function to remove student from course | So Yeun |  |  | ü
|  | 3.2 | Reduce student count from course attribute | So Yeun |  |  | ü
28 | Develop refund function to refund student fee | 28.1 | Recalculate course figures after student is withdrawn from the course | So Yeun |  |  | ü | Implemented with PBI 9
|  | 28.2 | Recalculate student owe fee | So Yeun |  |  | ü
37 | Update new cooking course enrolment fees | 37.1 | Update course fees to new amount | Wee Jueh |  |  | ü | Italian Cooking $450, Seafood $750
38 | Develop Develop function to update course enrolment fee | 38.1 | Update main console menu to inclue new function | Wee Jueh |  |  | ü
|  | 38.2 | Develop function to allow update of new course fees | Wee Jueh |  |  | ü
29 | Develop JUnit tests for major system functionality | 29.1 | Develop JUnit test for enrolment into course | Alex |  |  | ü
|  | 29.2 | Develop JUnit test to withdrawal from course | Alex |  |  | ü
|  | 29.3 | Develop JUnit test for testing user console input | Alex |  |  | ü
30 | Iterate through unit tests and debug till all tests pass | 30.1 | Perform all JUnit tests | Alex |  |  | ü
|  | 30.2 | Bug Fixes for any issues found | Alex |  |  | ü
31 | Refractor code forreadability and future extensibility | 31.1 | Refactor code according to Java style guide for better readability | Wee Jueh |  |  | ü
|  | 31.2 | Optimise code performace | Wee Jueh |  |  | ü
32 | Develop function to terminate application | 32.1 | Develop function to quit the application | So Yeun |  |  | ü | Implemented with PBI 6
34 | Create user documentation | 34.1 | Research on structure of documentation | So Yeun |  |  | ü
|  | 34.2 | Create user documentation | So Yeun |  |  | ü
35 | Create technical documentation | 35.1 | Research on document structure | Alex |  |  | ü
|  | 35.2 | Create technical documentation | Alex |  |  | ü
36 | Training of Course managers on system features | 36.1 | Plan training day for course managers | Edward |  |  | ü
|  | 36.2 | Conduct training on system features for course managers | Edward |  |  | ü

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #NAME? | #NAME?
| Previous Year | #NAME? | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!